## Sheet1
Stakeholder | Role | Power | Interest | Influence | Risks | Management Strategy | Communication | Contact Person | Contact Details | Preferred Communication Channels
Local Authorities | Provide land and regulatory support | High | High | High | Delays in approvals | Regular meetings and updates | Monthly progress reports | Jozef Kafka (Local Government Officer) | jozef.kafka@outlook,com +42192456789 | Emails, Virtual Meetings
Investors | Fund development projects | High | High | Medium | Lack of funding | Engage with tax incentives | Quarterly investor meetings | Natalia Matulova (Lead Investor) | natalia.matulova@investcorp.com, +421947654321 | Quarterly Reports, Emails
Young Families | Seek affordable housing | Low | High | High | Limited engagement | Create feedback channels | Surveys and community events | N/A | N/A | Surveys, Community Forums
Community Organizations | Advocate for local housing needs | Medium | High | Low | Limited resources | Collaborate on outreach initiatives | Informal meetings | Emilia Janusova (Community Manager) | emilia.janusova@outlook.com +42029384756 | Informal Meetings, Emails
Construction Firms | Build and renovate housing units | High | Medium | High | Project delays due to financing | Clear contracts and timelines | Regular updates on progress | David Horvat(Project Manager, Construction) | david.horvat@construct.com, +420602582586 | Weekly Reports, Virtual Meetings
Description of the File "Updated Affordable Housing for Young Families"
This file contains a stakeholder analysis for the project "Affordable Housing for Young Families." It presents detailed information about various stakeholder groups, their roles, levels of power, interest, and influence, as well as associated risks and management strategies.
Key Additions:
Contact Persons: Specific names and positions of key contact persons have been added to enhance communication personalization.
Contact Details: Email addresses and phone numbers are provided for easier communication with each stakeholder.
Communication Channels: Updated information on preferred communication channels for each group allows for more effective interaction.
This analysis serves as a foundation for strategic stakeholder management, which is a crucial element for the successful implementation of the project.